## Slide 1: Central high school Action Plan Racial equity
Timothy J. McKenna
President of Central High School

## Slide 2: Schoolwide assemblies on the topics of racism and racial bias supported by outside experts – Goal: next 6 weeks
Progress Update:
Amy Edelstein (Mindfulness) and Brendon Jobs (Diversity Director of Haverford School – Developing class assemblies regarding racial conflict, racial bias and conflict resolution
Faculty Professional Development sessions led by Dr. Ali Micheal – the co-founder of the Race Institute for k-12 Educators and the author of Raising Race Questions: Whiteneess, Inquiry and Education. More information can be found at alimichael.org.
Jeremy Bannett (Senior Associate Regional Director, Anti-Defamation League) offered programing for training anti-bias facilitators and ideas for community building activities with Cheltenham High School students
Randy Duque (Deputy Director, Philadelphia Commission on Human Relations: Community Relations Division) connected us with Dr. Anita Foeman (Founder and Primary Investigator, DNA Discussion Project). She is a professor of communications at West Chester University and a scholar of intercultural and organizational communication.

## Slide 3: CHS Administrative Team and student leaders will develop a professional development at which our students give their perspectives on racial issues at Central High School to the faculty in small group settings. – Goal: presentations given by the end of this school year.
Progress Update:
CHS Admin and Student Leaders are scheduled to meet on March 17, 2020 to plan the sharing sessions. Four student leaders will be selected to make the presentations.

## Slide 4: Reinstatement of the CHS Faculty-Student Advisory Council: an elected group of teachers and students who work together to solve school issues. – Goal: elections by the end of the year; reinstatement of council – September 2020
Progress Update:
AP Harrington and AP VanBuskirk are developing a plan to hold elections for student leaders and faculty members by the end of the school year.
Bylaws are being reviewed for the council as per the CHS Student Handbook

## Slide 5: Schoolwide assemblies related to social media usage – We will be contacting outside experts to support these presentations. Parents will be invited to attend. – Goal: April 2020
Progress Update:
Richard Guerry, a national speaker on social media usage, will be presenting to all classes during the week of April 13th. The title of his presentation is: Public and Permanent: Motivate Responsible Use of Technology & Prevent Digital Abuse! Parents are invited and encouraged to attend the presentation. His presentation is 1 hour 20 minutes long.
Schedule:
282 – Monday, April 13, 2020 – 8:00 am – 9:20 am
281 – Tuesday, April 14, 2020 – 8:00 am – 9:20 am
280 – Thursday, April 16, 2020 – 8:00 am – 9:20 am
279 – Friday, April 17, 2020 – 8:00 am – 9:20 am

## Slide 6: Explore the use of community building circles during homeroom to support our students and faculty members with making better personal connections and developing positive relationships. – Goal: training for selected staff and student leaders during summer 2020
Progress Update:
Dr. Abigail Gray, Deputy Chief of School Climate and Safety has been supporting us with plans to utilize community building circles to create weekly time to support our faculty and students with developing positive relationships.
School Climate and Safety trainer Josh Staub is offering a two-day training named “Relationships First”. The training will be offered in the summer. We are going to recruit teachers and students to participate to develop a team to conduct circles during advisory next year.

## Slide 7: Expand CHS Handbook Review for all students– Student/Admin panels will share all discipline regulations and harassment policy in detail and enable students to ask clarifying questions so that all expectations are presented in a clearer manner. – Goal: September 2020
Progress Update:
This is on the agenda to discuss on with student leaders on March 17, 2020 during our planning meeting

## Slide 8: Provide students a more diverse library of readings for our English and History curriculums. – Goal: research appropriate titles by end of school year / new additions to our catalog available for 2020-2021 school year
Progress Update:
This is on the agenda to discuss on with student leaders on March 17, 2020 during our planning meeting.
We will be identifying English / Social Studies teachers that can support us with selecting appropriate novels that celebrate cultures.